## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a user, I want to submit a ticket with title and description so that I can report technical issues | MUST HAVE | None |  | 3- Completed
Sprint 1 | Sprint 1 | US-002 | As a system, I want to validate and preprocess ticket descriptions so that noisy or invalid text does not affect classification | MUST HAVE | US-001 |  | 3- Completed
Sprint 1 | Sprint 1 | US-003 | As a system, I want to analyze ticket descriptions and categorize them automatically using an AI model | MUST HAVE | US-002 |  | 3- Completed
Sprint 2 | Sprint 2 | US-004 | As a system, I want to improve prediction accuracy by handling dataset imbalance so that all ticket categories are classified fairly | MUST HAVE | US-003 |  | 3- Completed
Sprint 2 | Sprint 2 | US-005 | As an admin, I want to evaluate model performance using suitable metrics so that classification quality can be measured effectively | SHOULD HAVE | US-003 |  | 3- Completed
Sprint 3 | Sprint 3 | US-006 | As an agent, I want to view categorized tickets in a dashboard so that I can work on assigned issues efficiently | MUST HAVE | US-003 |  | 3- Completed
Sprint 3 | Sprint 3 | US-007 | As a system, I want to generate real-time analytics for support metrics so that ticket trends can be monitored | SHOULD HAVE | US-006 |  | 3- Completed
Sprint 4 | Sprint 4 | US-008 | As an agent, I want to reassign tickets when required so that workload is balanced across the team | COULD HAVE | US-006 |  | 3- Completed
Sprint 4 | Sprint 4 | US-009 | As an admin, I want logging and performance optimization so that system errors can be detected and resolved quickly | SHOULD HAVE | US-003 |  | 3- Completed
Note on F1: Sumeet Kumar Barua08: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 136 | 12 | 12 | 10 | 10 | 11 | 10 | 11 | 10 | 9 | 13 | 6 | 6 | 11 | 4
SPRINT 1 BACKLOG
US-001 | T1-1 | Understand project scope and ticket workflow | 2026-01-05 | 2026-01-05 |  | Planning | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T1-2 | Attend mentor sessions on NLP & classification | 2026-01-06 | 2026-01-08 |  | Learning | 3- Completed | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T1-3 | Explore dataset structure & category distribution | 2026-01-09 | 2026-01-10 |  | Analysis | 3- Completed | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T1-4 | Identify preprocessing requirements | 2026-01-11 | 2026-01-11 |  | Planning | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T1-5 | Clean and normalize ticket text | 2026-01-12 | 2026-01-13 |  | Development | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
US-002 | T1-6 | Perform text vectorization | 2026-01-14 | 2026-01-15 |  | Development | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0
US-003 | T1-7 | Train baseline classification model | 2026-01-16 | 2026-01-17 |  | Development | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
US-003 | T1-8 | Test initial model predictions | 2026-01-18 | 2026-01-18 |  | Testing | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
SPRINT 2 BACKLOG
US-004 | T2-1 | Analyze dataset distribution | 2026-01-19 | 2026-01-19 |  | Analysis | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T2-2 | Apply class balancing techniques | 2026-01-20 | 21-Jan |  | Development | 3- Completed | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T2-3 | Retrain model with balanced dataset | 2026-01-22 | 23-Jan |  | Development | 3- Completed | 6 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T2-4 | Compare multiple ML algorithms | 2026-01-24 | 26-Jan |  | Development | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T2-5 | Evaluate precision, recall & F1-score | 2026-01-27 | 28-Jan |  | Evaluation | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0
US-005 | T2-6 | Finalize optimized model | 2026-02-01 | 1-Feb |  | Planning | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
SPRINT 3 BACKLOG
US-006 | T3-1 | Build backend API for model integration | 2026-02-02 | 2026-02-03 |  | Development | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T3-2 | Integrate trained model with API | 2026-02-04 | 2026-02-05 |  | Integration | 3- Completed | 6 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T3-3 | Test real-time prediction flow | 2026-02-06 | 2026-02-06 |  | Testing | 3- Completed | 4 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T3-4 | Design dashboard UI layout | 2026-02-07 | 2026-02-08 |  | Design | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T3-5 | Develop ticket display interface | 2026-02-09 | 2026-02-11 |  | Development | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-007 | T3-6 | Connect frontend with backend | 2026-02-12 | 2026-02-13 |  | Integration | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 |  | 0 | 0
US-007 | T3-7 | Implement filtering & sorting | 2026-02-14 | 2026-02-15 |  | Development | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0
SPRINT 4 BACKLOG
US-009 | T4-1 | Implement logging mechanism | 2026-02-16 | 2026-02-17 |  | Development | 3- Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T4-2 | Add global error handling | 2026-02-17 | 2026-02-18 |  | Development | 3- Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T4-3 | Optimize model loading time | 2026-02-19 | 2026-02-20 |  | Optimization | 3- Completed | 5 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T4-4 | Optimize database queries | 2026-02-20 | 2026-02-21 |  | Optimization | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T4-5 | Conduct end-to-end testing | 2026-02-22 | 2026-02-23 |  | Testing | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-009 | T4-6 | Final validation & documentation | 2026-02-24 | 2026-02-24 |  | Documentation | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
Note on D2: Sumeet Kumar Barua08: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Sumeet Kumar Barua08: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: Sumeet Kumar Barua08: This is the total task estimated in hours for all the user stories
Note on J3: Sumeet Kumar Barua08: Pending effort hours after completion of day 1 work
Note on K3: Sumeet Kumar Barua08: Pending effort hours after completion of day 2 work
Note on L3: Sumeet Kumar Barua08: Pending effort hours after completion of day 3 work
Note on M3: Sumeet Kumar Barua08: Pending effort hours after completion of day 4 work
Note on N3: Sumeet Kumar Barua08: Pending effort hours after completion of day 5 work
Note on O3: Sumeet Kumar Barua08: Pending effort hours after completion of day 6 work
Note on P3: Sumeet Kumar Barua08: Pending effort hours after completion of day 7 work
Note on Q3: Sumeet Kumar Barua08: Pending effort hours after completion of day 8 work
Note on R3: Sumeet Kumar Barua08: Pending effort hours after completion of day 9 work
Note on S3: Sumeet Kumar Barua08: Pending effort hours after completion of day 10 work
Note on T3: Sumeet Kumar Barua08: Pending effort hours after completion of day 11 work
Note on U3: Sumeet Kumar Barua08: Pending effort hours after completion of day 12 work
Note on V3: Sumeet Kumar Barua08: Pending effort hours after completion of day 13 work
Note on W3: Sumeet Kumar Barua08: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Dataset contained inconsistent and duplicate ticket entries | Performed data cleaning and standardized category labels
Sprint 1 | Day 10 | Baseline model accuracy was low | Analyzed confusion matrix and improved preprocessing strategy
Sprint 2 | Day 4 | Model accuracy inconsistent across categories | Applied class weighting and retrained the model
Sprint 2 | Day 8 | Overfitting observed in advanced model | Tuned hyperparameters and finalized optimized model
Sprint 3 | Day 4 | Backend API response delay during model integration | Optimized model loading and improved request handling
Sprint 3 | Day 8 | Frontend not displaying predicted category correctly | Fixed API response mapping and UI rendering logic
Sprint 4 | Day 4 | Slow prediction response on first request | Optimized model initialization process
Sprint 4 | Day 8 | Minor UI and validation edge case issues | Added input validation and conducted end-to-end testing

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 5-Jan-26 | 18-Jan-26 |  | Create a structured preprocessing pipeline | Starting model training before full dataset analysis | Understanding NLP fundamentals and dataset exploration | Document preprocessing steps clearly
2 | Sprint 1 | 5-Jan-26 | 18-Jan-26 |  | Perform early dataset validation | Ignoring class imbalance in initial experiments | Regular dataset visualization and analysis | Apply balancing methods in next sprint
3 | Sprint 2 | 19-Jan-26 | 1-Feb-26 |  | Compare multiple machine learning models | Depending on a single baseline model | Systematic evaluation using precision recall and F1-score | Finalize best performing algorithm
4 | Sprint 2 | 19-Jan-26 | 1-Feb-26 |  | Implement proper model saving strategy | Manual retraining for every test | Tracking performance metrics consistently | Use joblib for model persistence
5 | Sprint 3 | 2-Feb-26 | 15-Feb-26 |  | Build backend APIs before advanced UI work | Designing UI before backend stabilization | Incremental integration testing | Ensure stable API before UI scaling
6 | Sprint 3 | 2-Feb-26 | 15-Feb-26 |  | Improve responsive dashboard design | Ignoring edge case API responses | Frontend and backend validation checks | Add structured error handling
7 | Sprint 4 | 16-Feb-26 | 24-Feb-26 |  | Focus on performance optimization and logging late sprint | Skipping structured logging in early stages | End to end system testing before deployment | Implement logging indexing and validation improvements